## general_report
JIRA
Displaying 51 issues at 07/Jul/15 4:13 AM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Votes | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Linked Issues | Environment | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | Epic Status | Epic Color | Rank | Iteration | Test Sessions | Raised During | Story Points | Business Value | Sprint | Epic Name | Epic Link | [CHART] Date of First Response | Testing Status | Account | Team | Flagged | Epic/Theme
openFDA | OP-1 | Search based on drug name, return information on pregnancy and nursing risks associated to prescription drugs | Story | Done | Medium | Done | Shannon McHarg | James Deel [Administrator] | James Deel [Administrator] | 2015-06-19 09:13 | 2015-07-07 04:13 | 2015-06-29 08:24 | 2015-06-29 08:24 |  |  |  |  | 0 | 1 | [5 empty] | OP-10, OP-18, OP-20, OP-34 | [12 empty] | 0¦hzzzzz: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-2 | Search based on medical condition, return information on pregnancy and nursing risks associated to prescription drugs - DROPPED FEATURE | Story | Done | Medium | Done | Shannon McHarg | James Deel [Administrator] | James Deel [Administrator] | 2015-06-19 09:14 | 2015-06-19 09:40 | 2015-06-22 10:07 | 2015-06-22 10:06 |  |  |  |  | 0 | 1 | [5 empty] | OP-11, OP-21, OP-22 | [12 empty] | 0¦i00007: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-3 | Create Home page | Story | Done | Medium | Done | Shannon McHarg | James Deel [Administrator] | James Deel [Administrator] | 2015-06-19 09:17 | 2015-06-19 09:41 | 2015-06-29 08:24 | 2015-06-29 08:24 |  |  |  |  | 0 | 1 | [5 empty] | OP-12, OP-23, OP-24, OP-30, OP-31, OP-32, OP-33 | [12 empty] | 0¦i0000f: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-4 | Save past searches in a Favorites type bucket | Story | To Do | Medium | Unresolved | Unassigned | James Deel [Administrator] | James Deel [Administrator] | 2015-06-19 09:20 |  | 2015-06-19 09:20 | [5 empty] | 0 | 1 | [5 empty] | OP-13 | [12 empty] | 0¦i0000n: | None | [8 empty] | Not Started | None | None
openFDA | OP-5 | Provide push notifications can be added from the FDA database to alert users to new risks | Story | To Do | Medium | Unresolved | Unassigned | James Deel [Administrator] | James Deel [Administrator] | 2015-06-19 09:22 |  | 2015-06-19 09:22 | [5 empty] | 0 | 1 | [5 empty] | OP-14 | [12 empty] | 0¦i0000v: | None | [8 empty] | Not Started | None | None
openFDA | OP-6 | Provide a user profile capability so push notifications, searches, and other information can be tailored | Story | To Do | Medium | Unresolved | Unassigned | James Deel [Administrator] | James Deel [Administrator] | 2015-06-19 09:23 |  | 2015-06-19 09:23 | [5 empty] | 0 | 1 | [5 empty] | OP-15 | [12 empty] | 0¦i00013: | None | [8 empty] | Not Started | None | None
openFDA | OP-7 | Create Data Model | Story | Done | Medium | Done | Scott Prenger | James Deel [Administrator] | James Deel [Administrator] | 2015-06-19 09:31 | 2015-06-20 08:00 | 2015-06-29 12:41 | 2015-06-29 12:41 |  |  |  |  | 0 | 2 | [5 empty] | OP-8, OP-9, OP-16, OP-17 |  |  | Define data layer and determine what fields are available in the API (many do not show up in the downloadable file). Also, we would like to see what kind of data we get back to assess how usable it is in its current form. Finally, we would like to know if there are periodic updates to this table that we could use as a feature to alert the consumer about changes or updates. | [9 empty] | 0¦i0000j: | None |  |  |  |  | open FDA Sprint 1 |  |  | 2015-06-19 14:55 | Not Started | None | None
openFDA | OP-8 | OP-7 Data Fields to Return | Sub-task | Done | Medium | Done | Unassigned | James Deel [Administrator] | James Deel [Administrator] | 2015-06-19 09:34 | 2015-07-07 04:07 | 2015-07-07 04:07 | 2015-07-07 04:07 |  |  |  |  | 0 | 1 | [8 empty] | use_in_specific_populations pregnancy teratogenic_effects nonteratogenic_effects labor_and_delivery nursing_mothers carcinogenesis_and_mutagenesis_and_impairment_of_fertility indications_and_usage dosage_forms_and_strengths description purpose active_ingredient | [9 empty] | 0¦i0001j: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-9 | OP-7 Data Fields for Return | Sub-task | Done | Medium | Done | Unassigned | James Deel [Administrator] | James Deel [Administrator] | 2015-06-19 09:36 | 2015-07-07 04:08 | 2015-07-07 04:08 | 2015-07-07 04:08 |  |  |  |  | 0 | 1 | [8 empty] | We’ll also need the fields listed in the following sections on this page: https://open.fda.gov/drug/label/reference/ · Adverse effects and interactions · Indications, usage, and dosage · Patient information · Special populations · Nonclinical toxicology · References · Warnings and precautions · Other fields | [9 empty] | 0¦i0001r: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-10 | OP-1 Create Wireframe | Sub-task | Done | Medium | Done | Shannon McHarg | James Deel [Administrator] | James Deel [Administrator] | 2015-06-19 09:37 | 2015-06-19 09:37 | 2015-06-22 14:36 | 2015-06-22 08:54 |  |  |  |  | 0 | 2 | [6 empty] | OP-16 |  | Model page with layout If search returns an exact match to either a [brand_name] or a [generic_name] bypass this page and go straight to the Drug Details page. *Fields* Risk level maps to [teratogenic_effects] field. Low maps to Pregnancy Category A Low* maps to Pregnancy Category B Med maps to Pregnancy Category C Med* maps to Pregnancy Category D High maps to Pregnancy Category X [brand_name] Users can access drug details page by linking from search results. [generic_name] [indications_and_usage] Additional characters in the [indications_and_usage] field will display on larger viewports when they start to fit without wrapping onto a fourth row. 340 chars on desktop, 155 chars on tablet, 125 chars on mobile. REMOVE number and label from beginning of field "1 INDICATIONS AND USAGE" in Topamax example. REMOVE all references to other sections "[see Clinical Studies (14.3)]" is an example from the Topamax example. Users can sort by relevancy, risk level, and drug name. Default sort is by relevancy. | [9 empty] | 0¦i0001z: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-11 | OP-2 Create Wireframe - DROPPED FEATURE | Sub-task | Done | Lowest | Done | Shannon McHarg | James Deel [Administrator] | James Deel [Administrator] | 2015-06-19 09:38 | 2015-06-19 09:38 | 2015-06-22 08:38 | 2015-06-22 08:38 |  |  |  |  | 0 | 2 | [6 empty] | OP-16 |  | Model page with layout Searches matches for drug names that go with the keyword entered. Users can access drug details page by linking from search results. Additional fields will display on larger viewports when they start to fit. Users can sort by relevancy, risk level, and drug name. Default sort is by risk level. Risk level maps to [teratogenic_effects] field. Level 1 maps to Pregnancy Category A Low Data maps to Pregnancy Category B Level 2 maps to Pregnancy Category C Level 3 maps to Pregnancy Category D Level 4 maps to Pregnancy Category X | [9 empty] | 0¦i00027: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-12 | OP-3 Create Wireframe | Sub-task | Done | Medium | Done | Shannon McHarg | James Deel [Administrator] | James Deel [Administrator] | 2015-06-19 09:38 | 2015-06-19 09:38 | 2015-06-22 08:38 | 2015-06-22 08:38 |  |  |  |  | 0 | 2 | [6 empty] | OP-16 |  | Model page with layout Users can search by prescription drug. Searches for matches to the products listed in the [brand_name] or [generic_name] fields. Present information about the application and informing users that we use openFDA data. Present lists of common drugs. This list is TBD. Present a list of drugs that have recently been updated in the database. Display 3 drugs with the most recent updates to the [recent_major_changes] field. | [9 empty] | 0¦i0002f: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-13 | OP-4 Create Wireframe | Sub-task | To Do | Medium | Unresolved | Unassigned | James Deel [Administrator] | James Deel [Administrator] | 2015-06-19 09:38 | 2015-06-19 09:38 | 2015-06-19 09:38 | [5 empty] | 0 | 1 | [8 empty] | Model page with layout | [9 empty] | 0¦i0002n: | None | [8 empty] | Not Started | None | None
openFDA | OP-14 | OP-5 Create Wireframe | Sub-task | To Do | Medium | Unresolved | Unassigned | James Deel [Administrator] | James Deel [Administrator] | 2015-06-19 09:39 | 2015-06-19 09:39 | 2015-06-19 09:39 | [5 empty] | 0 | 1 | [8 empty] | Model page with layout | [9 empty] | 0¦i0002v: | None | [8 empty] | Not Started | None | None
openFDA | OP-15 | OP-6 Create Wireframe | Sub-task | To Do | Medium | Unresolved | Unassigned | James Deel [Administrator] | James Deel [Administrator] | 2015-06-19 09:39 | 2015-06-19 09:39 | 2015-06-19 09:39 | [5 empty] | 0 | 1 | [8 empty] | Model page with layout | [9 empty] | 0¦i00033: | None | [8 empty] | Not Started | None | None
openFDA | OP-16 | OP-7 Research API to determine if desired fields are available | Sub-task | Done | Medium | Done | Unassigned | James Deel [Administrator] | James Deel [Administrator] | 2015-06-19 11:17 | 2015-07-07 04:06 | 2015-07-07 04:06 | 2015-07-07 04:06 |  |  |  |  | 0 | 2 | [6 empty] | OP-10, OP-12, OP-19, OP-11 |  | Use SQL studio to research API | [9 empty] | 0¦i0003b: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-17 | OP-7 Obtain API key | Sub-task | Done | High | Done | Scott Prenger | Scott Prenger | Scott Prenger | 2015-06-19 11:34 |  | 2015-06-19 11:34 | 2015-06-19 11:34 |  |  |  |  | 0 | 1 | [8 empty] | An API Key is required for access to the API. ovNVdm7TO3IlzJr8ABOS6Zpdad70SNsBV3NW757e | [9 empty] | 0¦i0003j: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-18 | OP-1 Create visual design comp | Sub-task | Done | Medium | Done | Dana Travis | Yana Beranek | Yana Beranek | 2015-06-19 13:53 |  | 2015-06-22 09:47 | 2015-06-22 09:47 |  |  |  |  | 0 | 1 | _thumb_10000.png _thumb_10002.png _thumb_10004.png | [7 empty] | Acceptance criteria psd is created, approved and cut | [9 empty] | 0¦i0003r: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-19 | OP-27 Review detailed information about specific drug selected from search results | Sub-task | Done | Medium | Done | Shannon McHarg | Yana Beranek | Yana Beranek | 2015-06-19 13:56 | 2015-06-29 15:32 | 2015-06-29 15:32 | 2015-06-22 09:37 |  |  |  |  | 0 | 2 | [6 empty] | OP-16 |  | Users can view details of the drug, risk rating, and links to alternative drugs for the same condition. *Fields* [brand_name] Users can access drug details page by linking from search results. [generic_name] Risk Level maps to [teratogenic_effects] field. Low maps to Pregnancy Category A - Description: “Human studies have shown no risk of fetal harm.” Low* maps to Pregnancy Category B - Description: “Animal studies have not shown risks for fetal harm. Studies have not been done in humans.” Med maps to Pregnancy Category C - Description: “Animal studies show high risk for fetal harm. Studies have not been done in humans. Consult a doctor for guidance before taking this drug while pregnant” Med* maps to Pregnancy Category D - Description: “Human studies show high risk for fetal harm. Consult a doctor for guidance before taking this drug while pregnant.” High maps to Pregnancy Category X - Description: "Human or animal studies show very high risk for fetal harm. The risk of the use of the drug in a pregnant woman clearly outweighs any possible benefit." Use During Pregnancy: [teratogenic_effects] REMOVE risk level and warning at the beginning of the field. "Pregnancy Category D. [see Warnings and Precautions (5.6)] ' REMOVE all references to other sections "[see Clinical Studies (14.3)]" is an example from the Topamax example. Use During Labor and Delivery: [labor_and_delivery] REMOVE "8.2 Labor and Delivery " from the beginning. REMOVE all references to other sections "[see Clinical Studies (14.3)]" is an example from the Topamax example. Use While Nursing: [nursing_mothers] REMOVE "8.3 Nursing Mothers " from the beginning. REMOVE all references to other sections "[see Clinical Studies (14.3)]" is an example from the Topamax example. Usage: [indications_and_usage] REMOVE number and label from beginning of field "1 INDICATIONS AND USAGE" in Topamax example. REMOVE all references to other sections "[see Clinical Studies (14.3)]" is an example from the Topamax example. Ingredients: [spl_product_data_elements] REMOVE brand name and generic name from the beginning. "Topamax topiramate " Alternatives Use [pharm_class_moa], [pharm_class_cs], [pharm_class_pe], [pharm_class_epc] to determine alternative drugs. More/Less Treatment For any field that contains more than 580 characters, truncate at 580 and display a More link that expands to display the full contents of the field with a Less link. See the Usage section in the wireframe for how this should function. | [9 empty] | 0¦i0000b: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-20 | OP-1 Apply visual design | Sub-task | Done | Medium | Done | Dana Travis | Yana Beranek | Yana Beranek | 2015-06-19 14:09 |  | 2015-06-23 08:50 | 2015-06-23 08:50 |  |  |  |  | 0 | 1 | [8 empty] | Acceptance criteria Developed screen matches visual comp | [9 empty] | 0¦i0003z: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-21 | OP-2 Crete visual design comp - DROPPED FEATURE | Sub-task | Done | Medium | Done | Dana Travis | Yana Beranek | Yana Beranek | 2015-06-19 14:09 |  | 2015-06-22 08:39 | 2015-06-22 08:39 |  |  |  |  | 0 | 1 | [8 empty] | Acceptance criteria pdf file is created, approved and cut | [9 empty] | 0¦i00047: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-22 | OP-2 Apply visual design - DROPPED FEATURE | Sub-task | Done | Medium | Done | Dana Travis | Yana Beranek | Yana Beranek | 2015-06-19 14:10 |  | 2015-06-22 08:39 | 2015-06-22 08:39 |  |  |  |  | 0 | 1 | [8 empty] | Acceptance criteria Developed screen matches visual design comp | [9 empty] | 0¦i0004f: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-23 | OP-3 Create visual design comp | Sub-task | Done | Medium | Done | Dana Travis | Yana Beranek | Yana Beranek | 2015-06-19 14:11 |  | 2015-06-22 09:48 | 2015-06-22 09:48 |  |  |  |  | 0 | 1 | _thumb_10006.png _thumb_10008.png _thumb_10010.png | [7 empty] | Acceptance criteria psd file is created, approved and cut | [9 empty] | 0¦i0004n: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-24 | OP-3 Apply visual design | Sub-task | Done | Medium | Done | Dana Travis | Yana Beranek | Yana Beranek | 2015-06-19 14:12 |  | 2015-06-23 09:04 | 2015-06-23 09:04 |  |  |  |  | 0 | 1 | [8 empty] | Acceptance criteria Developed screen matches visual design comp | [9 empty] | 0¦i0004v: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-25 | Configure MS Azure Server Environment | Task | Done | High | Done | James Deel [Administrator] | James Deel [Administrator] | James Deel [Administrator] | 2015-06-22 08:51 | 2015-06-29 15:33 | 2015-06-23 13:27 | 2015-06-23 13:27 |  |  |  |  | 0 | 1 | [8 empty] | Configure Web/App server for openFDA app. | [9 empty] | 0¦i0005n: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-26 | OP-27 Drug Details: Visual Design Comp | Sub-task | Done | Medium | Done | Dana Travis | Shannon McHarg | Shannon McHarg | 2015-06-22 09:50 | 2015-06-29 15:32 | 2015-06-29 15:32 | 2015-06-22 09:52 |  |  |  |  | 0 | 2 | _thumb_10017.png _thumb_10015.png _thumb_10013.png | [5 empty] | OP-27 |  | Create comps for Drug Details page. | [9 empty] | 0¦i00053: | None |  |  |  |  | open FDA Sprint 1 |  |  | 2015-06-22 10:26 | Not Started | None | None
openFDA | OP-27 | Create Drug Details Page | Story | Done | Medium | Done | Unassigned | Shannon McHarg | Shannon McHarg | 2015-06-22 09:52 | 2015-06-29 15:32 | 2015-06-29 20:06 | 2015-06-29 20:06 |  |  |  |  | 0 | 1 | [5 empty] | OP-19, OP-26, OP-28 | OP-26 | [9 empty] | To Do | ghx-label-1 | 0¦i0005b: | None |  |  |  |  | open FDA Sprint 1 | Create Drug Details Page |  |  | Not Started | None | None
openFDA | OP-28 | OP-27 Drug Details: Apply Visual Design | Sub-task | Done | Medium | Done | Dana Travis | Shannon McHarg | Shannon McHarg | 2015-06-22 10:03 | 2015-06-29 15:33 | 2015-06-29 15:33 | 2015-06-23 08:49 |  |  |  |  | 0 | 1 | [8 empty] | Apply visual design. | [9 empty] | 0¦i0005j: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-29 | Remote testing of the clickable axure wireframes to gain user feedback | Epic | To Do | Medium | Unresolved | Unassigned | Yana Beranek | Yana Beranek | 2015-06-22 10:53 |  | 2015-06-22 10:53 | [5 empty] | 0 | 0 | [16 empty] | To Do | ghx-label-3 | 0¦i0005r: | None | [5 empty] | Conduct usability testing of design to gain user insights |  |  | Not Started | None | None
openFDA | OP-30 | OP-3 Develop study guide for UX Testing | Sub-task | Done | Medium | Done | Yana Beranek | Yana Beranek | Yana Beranek | 2015-06-22 10:54 |  | 2015-06-23 09:05 | 2015-06-23 09:05 |  |  |  |  | 0 | 1 | [8 empty] | Acceptance criteria Study guide approved by researcher and designer | [9 empty] | 0¦i0005z: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-31 | OP-3 Recruit users for testing | Sub-task | Done | Medium | Done | Yana Beranek | Yana Beranek | Yana Beranek | 2015-06-22 10:54 |  | 2015-06-23 09:10 | 2015-06-23 09:10 |  |  |  |  | 0 | 1 | [8 empty] | Acceptance A minimum of 6 users recruited from target audience | [9 empty] | 0¦i00067: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-32 | OP-3 Revise design based on user feedback | Sub-task | Done | Medium | Done | Shannon McHarg | Yana Beranek | Yana Beranek | 2015-06-22 10:55 |  | 2015-06-22 14:39 | 2015-06-22 14:39 |  |  |  |  | 0 | 1 | [8 empty] | Acceptance criteria Develop recommendations for enhancements and revisions to design based on user feedback SM: The only change to the design we needed to make was to revise the risk level scale. See the wireframe tickets for Search Results and Drug Details for revised rating scale. | [9 empty] | 0¦i0006f: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-33 | OP-3 Conduct UX testing | Sub-task | Done | Medium | Done | Yana Beranek | Yana Beranek | Yana Beranek | 2015-06-23 09:10 |  | 2015-06-23 09:12 | 2015-06-23 09:12 |  |  |  |  | 0 | 1 | [18 empty] | 0¦i0006n: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-34 | OP-1 Create icon for "Unknown Value" | Sub-task | Done | Medium | Done | Dana Travis | Yana Beranek | Yana Beranek | 2015-06-24 12:15 |  | 2015-06-24 13:59 | 2015-06-24 13:55 |  |  |  |  | 0 | 3 | _thumb_10021.png | [7 empty] | Data is returning unknown values. Need an additional icon to alert users to this status. | [9 empty] | 0¦i0006v: | None |  |  |  |  | open FDA Sprint 1 |  |  | 2015-06-24 13:49 | Not Started | None | None
openFDA | OP-35 | Usability Testing | Story | Done | Medium | Done | Yana Beranek | Yana Beranek | Yana Beranek | 2015-06-24 12:19 |  | 2015-07-01 11:56 | 2015-07-01 11:56 |  |  |  |  | 0 | 1 | [5 empty] | OP-36, OP-37, OP-38 |  |  | Conduct usability testing on live prototype | [9 empty] | 0¦i00073: | None | [8 empty] | Not Started | None | None
openFDA | OP-36 | OP-35 Recruit users for testing | Sub-task | Done | Medium | Done | Yana Beranek | Yana Beranek | Yana Beranek | 2015-06-24 12:19 |  | 2015-06-29 16:16 | 2015-06-29 16:16 |  |  |  |  | 0 | 1 | [18 empty] | 0¦i0007b: | None | [8 empty] | Not Started | None | None
openFDA | OP-37 | OP-35 Develop study guide for ux testing | Sub-task | Done | Medium | Done | Yana Beranek | Yana Beranek | Yana Beranek | 2015-06-24 12:20 |  | 2015-07-01 11:53 | 2015-07-01 11:53 |  |  |  |  | 0 | 1 | [18 empty] | 0¦i0007j: | None | [8 empty] | Not Started | None | None
openFDA | OP-38 | OP-35 Document ux testing findings and develop recommendations | Sub-task | Done | Medium | Done | Yana Beranek | Yana Beranek | Yana Beranek | 2015-06-24 12:20 |  | 2015-07-01 11:54 | 2015-07-01 11:54 |  |  |  |  | 0 | 1 | [8 empty] | Results of this set of testing will inform v2 of BabySafe Rx | [9 empty] | 0¦i0007r: | None | [8 empty] | Not Started | None | None
openFDA | OP-39 | Incorporate Inversion of Control Design Pattern into code | Task | Done | Medium | Done | Scott Prenger | Scott Prenger | Scott Prenger | 2015-06-27 13:53 |  | 2015-06-27 14:02 | 2015-06-27 14:00 |  |  |  |  | 0 | 1 |  |  | 0 | 3600 |  |  |  |  | Demonstrate IoC pattern in code |  | 100% | 100% | 3600 | 0 |  |  |  |  | 0¦i0007z: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-40 | Incorporate Log4Net logging into the Aplication | Task | Done | Medium | Done | Scott Prenger | Scott Prenger | Scott Prenger | 2015-06-27 13:54 |  | 2015-06-29 12:41 | 2015-06-29 12:41 |  |  |  |  | 0 | 1 | [8 empty] | Log errors and informational messages using Log4Net. | [9 empty] | 0¦i00087: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-41 | Create Unit tests | Task | Done | Medium | Done | Scott Prenger | Scott Prenger | Scott Prenger | 2015-06-27 13:55 |  | 2015-06-29 12:41 | 2015-06-29 12:41 |  |  |  |  | 0 | 1 | [8 empty] | Create Unit tests | [9 empty] | 0¦i0008f: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-42 | Use JQuery DataTable to display query results | Task | Done | Medium | Done | Scott Prenger | Scott Prenger | Scott Prenger | 2015-06-27 13:59 | 2015-07-07 04:12 | 2015-06-29 12:41 | 2015-06-29 12:41 |  |  |  |  | 0 | 1 | [8 empty] | Use JQuery DataTable to display the results with sortable headers, paging, etc. | [9 empty] | 0¦i00083: | None |  |  |  |  | open FDA Sprint 1 |  |  |  | Not Started | None | None
openFDA | OP-43 | No Human Data Key Should Only Display for Med* and Low* Risk Levels | Bug | Done | Medium | Done | Scott Prenger | Shannon McHarg | Shannon McHarg | 2015-06-29 08:26 |  | 2015-06-29 11:11 | 2015-06-29 11:11 |  |  |  |  | 0 | 2 | [8 empty] | The "*No human data" key is displaying for all risk levels on the Drug Details page, but it should only display for Med* and Low* levels. | [9 empty] | 0¦i0008n: | None | [7 empty] | 2015-06-29 10:01 | Not Started | None | None
openFDA | OP-44 | Search Results Cutting Off on Mobile | Bug | In Progress | Medium | Unresolved | Scott Prenger | Shannon McHarg | Shannon McHarg | 2015-06-29 08:30 |  | 2015-06-29 16:09 | [5 empty] | 0 | 2 | _thumb_10100.png | [7 empty] | The search results are cutting off on the left on mobile. | [9 empty] | 0¦i0008v: | None | [7 empty] | 2015-06-29 16:01 | Not Started | None | None
openFDA | OP-45 | Collapse Sections on Drug Details Page | Bug | Done | Medium | Done | Scott Prenger | Shannon McHarg | Shannon McHarg | 2015-06-29 08:34 |  | 2015-06-29 14:57 | 2015-06-29 14:57 |  |  |  |  | 0 | 2 | [8 empty] | all the sections on the Drug Details page should use the Read More link when the characters exceed 580. Not just the Usage section. More/Less Treatment For any field that contains more than 580 characters, truncate at 580 and display a More link that expands to display the full contents of the field with a Less link. See the Usage section in the wireframe for how this should function. | [9 empty] | 0¦i00093: | None | [7 empty] | 2015-06-29 14:01 | Not Started | None | None
openFDA | OP-46 | Amoxil Link on Homepage | Bug | Done | Medium | Done | Scott Prenger | Shannon McHarg | Shannon McHarg | 2015-06-29 08:35 | 2015-06-29 08:35 | 2015-06-29 11:11 | 2015-06-29 11:11 |  |  |  |  | 0 | 2 | [8 empty] | The Amoxil link on the home page doesn’t return any results. Can you have it bring up results for “Amoxicillin”? | [9 empty] | 0¦i0009b: | None | [7 empty] | 2015-06-29 10:00 | Not Started | None | None
openFDA | OP-47 | Hyperlink Underlines | Bug | In Progress | Medium | Unresolved | Scott Prenger | Shannon McHarg | Shannon McHarg | 2015-06-29 08:37 | 2015-06-29 13:30 | 2015-06-29 14:18 | [5 empty] | 0 | 2 | [8 empty] | All hyperlinks need to be underlined. Right now they just have a rollover state. | [9 empty] | 0¦i0009j: | None | [7 empty] | 2015-06-29 09:59 | Not Started | None | None
openFDA | OP-48 | Search icon has unwanted box shadow | Bug | In Progress | Medium | Unresolved | Scott Prenger | Dana Travis | Dana Travis | 2015-06-29 09:35 |  | 2015-06-29 16:09 | [5 empty] | 0 | 2 | _thumb_10101.png | [7 empty] | Seems to be only happening in Chrome and Safari. See attached screen shot. | [9 empty] | 0¦i0009r: | None | [7 empty] | 2015-06-29 16:09 | Not Started | None | None
openFDA | OP-49 | Drug Details: Need to display information for Unknown Risk level | Bug | Done | Medium | Done | Scott Prenger | Shannon McHarg | Shannon McHarg | 2015-06-29 11:12 |  | 2015-06-29 13:20 | 2015-06-29 13:20 |  |  |  |  | 0 | 2 | _thumb_10102.png | [7 empty] | Add the risk level icon and this text to the detail page for drugs with unknown risk level. "The risk level of this drug is unknown." | [9 empty] | 0¦i0009z: | None | [7 empty] | 2015-06-29 12:40 | Not Started | None | None
openFDA | OP-50 | Search Results: Sort Functionality Doesn't Work | Story | To Do | Medium | Unresolved | Scott Prenger | Shannon McHarg | Shannon McHarg | 2015-06-29 11:18 |  | 2015-06-29 14:12 | [5 empty] | 0 | 3 | [8 empty] | The column headers for risk level and drug name should sort the results. Risk Level 1st click, sort by ascending risk level Low, Low*, Med, Med*, High, Unknown 2nd click, sort by descending risk level, Unknown, High, Med*, Med, Low*, Low Drug Name 1st click, sort by ascending alpha order (A-Z) 2nd click, sort by descending alpha order (Z-A) - Can't confirm whether the drug name sort is working, since all the results I've seen have the same drug name. | [9 empty] | 0¦i000a7: | None | [7 empty] | 2015-06-29 12:29 | Not Started | None | None
openFDA | OP-52 | Show/Hide functionality not displaying correcting on window resize | Bug | To Do | Medium | Unresolved | Scott Prenger | Dana Travis | Dana Travis | 2015-07-01 11:59 | 2015-07-07 04:12 | 2015-07-01 11:59 | [5 empty] | 0 | 1 | _thumb_10112.png _thumb_10113.png _thumb_10114.png | [6 empty] | Chrome and IE11 | Show/Hide functionality is not displaying correctly when the browser window is resized smaller. The show/hide icons and prescription names are hidden at the smallest window size. Technically, functionality is not needed and could probably be removed so that the site functions like Safari (see attached screenshots). | [9 empty] | 0¦i000e7: | None | [8 empty] | Not Started | None | None
Generated at Tue Jul 07 04:13:56 CDT 2015 by James Deel [Administrator] using JIRA 6.5-OD-08-001#65007-sha1:1fc98468dfd18a5f35861f5c2ab67219b6b6f2f6.